## User Stories
ID | Area | Feature | Reference | User Story | Expected Behaviour | Invocation | Edge Cases / Validation | Phase 1 Status | Phase 2 Test Result | Errors Found | Phase 3 Fix | Phase 4 Retest
US-001 | Research MCP | Create research job | mcp_server.create_research_job | As an AI host, I give Oyster a plain-language brief so it returns a structured research plan and a persisted job. | build_plan() runs; a research_jobs row is created; returns {job_id, created_at, plan} with questions, entities, query families, recommended sources, clarifications. | create_research_job(brief, decision, market, time_horizon, audience, deliverable, required_sources, exclusions) | Brief under 12 chars raises 'enough detail'. Non-gaming brief must NOT pull twitch/kick. | Documented | PASS |  |  | PASS (re-verified green)
US-002 | Research MCP | Add evidence | mcp_server.add_evidence | As a host, I store a finding with provenance so it appears in the dossier. | Inserts research_evidence with content_hash dedup; published_at parsed from ISO; returns {evidence_id, collected_at}. | add_evidence(job_id, source_type, url, title, excerpt, author, published_at, query, metadata) | Duplicate (job_id, source_type, url, excerpt) updates collected_at, no dup row. Bad ISO published_at raises. | Documented | PASS |  |  | PASS (re-verified green)
US-003 | Research MCP | Fetch RSS | mcp_server.fetch_rss | As a host, I collect matching entries from a public feed. | Fetches feed, stores entries matching any query term as source_type=rss, logs raw payload; returns {feed_url, matched, items, raw_response_id}. | fetch_rss(job_id, feed_url, query_terms, limit) | Non-public/redirect-to-private URL rejected. Empty query_terms stores all. feedparser.parse used. | Documented | PASS | F4 (data quality, found in live Spider-Man run): feed summaries with HTML (e.g. Google News) were stored as raw <a> markup instead of readable text. | Added _plain_text() to strip tags + unescape entities; applied to RSS title/excerpt/author. | PASS (live re-run shows clean headlines; test_feed_html_is_reduced_to_readable_text)
US-004 | Research MCP | Search X | mcp_server.search_x | As a host, I search recent X posts via official API. | With bearer token, queries X recent search, stores posts as source_type=x; without token returns not_configured with fallbacks. | search_x(job_id, query, max_results) | No token -> {not_configured:true, connector:x_official, fallbacks:[...]}, not an error. | Documented | PASS |  |  | PASS (re-verified green)
US-005 | Research MCP | Inspect Discord invite | mcp_server.inspect_discord_invite | As a host, I capture public metadata for a Discord invite. | Resolves invite code, GETs invite with counts, stores guild name/member/presence as source_type=discord. | inspect_discord_invite(job_id, invite_url_or_code) | Bad code raises 'invite code or ... URL'. 404 raises 'invalid or expired'. | Documented | PASS |  |  | PASS (re-verified green)
US-006 | Research MCP | Run Apify actor | mcp_server.run_apify_actor | As a host, I run a chosen Apify Actor for Reddit/X/other sources. | With token, runs actor run-sync-get-dataset-items, stores rows; without token returns not_configured. | run_apify_actor(job_id, actor_id, actor_input, source_type, limit) | No token -> not_configured(apify). Empty actor_id raises 'Choose an Apify Actor ID'. | Documented | PASS |  |  | PASS (re-verified green)
US-007 | Research MCP | Search Twitch | mcp_server.search_twitch | As a host, I search arbitrary Twitch channels/topics. | With client id+secret, OAuth then search/channels, stores results; without creds returns not_configured(twitch). | search_twitch(job_id, query, limit) | No creds -> not_configured with fallbacks (apify/crawl/capture). OAuth token logged as oauth_token (redacted). | Documented | PASS |  |  | PASS (re-verified green)
US-008 | Research MCP | Search Kick | mcp_server.search_kick | As a host, I search current Kick streams. | With creds, OAuth then paginate livestreams filtered by query; without creds returns not_configured(kick). | search_kick(job_id, query, pages) | No creds -> not_configured. Token redacted. | Documented | PASS |  |  | PASS (re-verified green)
US-009 | Research MCP | Read Discord channel | mcp_server.read_discord_channel | As a host, I read messages from a channel the bot can access. | With bot token, reads channel + messages, stores non-empty messages as source_type=discord_message; without token not_configured. | read_discord_channel(job_id, channel_id, limit) | No token -> not_configured(discord_messages). 403 raises grant-permission guidance. | Documented | PASS |  |  | PASS (re-verified green)
US-010 | Research MCP | Crawl web page | mcp_server.crawl_web_page | As a host, I extract readable text + links from a public page. | Validates public URL, fetches via Scrapling, stores text + up to 100 links as source_type=web, logs raw payload. | crawl_web_page(job_id, url, query) | Private/local/reserved targets rejected (SSRF). HTTP>=400 raises. No extractable text raises with fallback hint. | Documented | PASS |  |  | PASS (re-verified green)
US-011 | Research MCP | Get dossier | mcp_server.get_research_dossier | As a host, I retrieve a job's evidence grouped with coverage and gaps. | Returns {job, evidence[], coverage{source:count}, gaps[]}; gaps = recommended sources with zero evidence. | get_research_dossier(job_id) | Unknown job_id raises 'was not found'. content_hash stripped from output. | Documented | PASS |  |  | PASS (re-verified green)
US-012 | Research MCP | List jobs | mcp_server.list_research_jobs | As a host, I list recent jobs to resume prior work. | Returns up to N recent jobs (id, brief, decision, status, timestamps) ordered by updated_at desc. | list_research_jobs(limit) | limit clamped 1..100. | Documented | PASS |  |  | PASS (re-verified green)
US-013 | Research MCP | Connector status | mcp_server.connector_status | As a host, I check which connectors are ready and how to set up or fall back. | Returns per-connector {ready, setup, fallbacks/scope...} derived from CONNECTOR_GUIDES + READY_CHECKS. | connector_status() | Never returns secret values. twitch/kick/apify/discord_messages all include fallbacks. | Documented | PASS |  |  | PASS (re-verified green)
US-014 | Research MCP | Export research report | mcp_server.export_research_report | As a host, I export a job to a folder of files. | Writes report.md/html, evidence.json/csv, raw_responses.jsonl to output/research-job-<id>-<slug>/; returns {folder, files, evidence_count, raw_count}. | export_research_report(job_id) | Pipes in cells escaped; CSV formula-injection guarded; output_dir anchored to project root. | Documented | PASS |  |  | PASS (re-verified green)
US-015 | Research MCP | Browser capture mission | mcp_server.get_browser_capture_mission | As a host, I turn a brief into browser-capture terms/questions. | Returns {job_id, brief, research_questions, look_for terms, exclusions, instructions} for the active job. | get_browser_capture_mission(job_id) | Only active jobs; unknown/inactive job raises 'was not found'. | Documented | PASS |  |  | PASS (re-verified green)
US-016 | Research MCP | Request traffic session | mcp_server.request_browser_traffic_session | As a host, I ask the researcher to approve a domain-scoped traffic capture session. | Creates a 'requested' capture_sessions row and returns it plus human instructions to approve+poll. | request_browser_traffic_session(job_id, domain, reason) | Domain normalized (no scheme/port/path/IP/localhost). Duplicate live session rejected. Inactive job rejected. | Documented | PASS |  |  | PASS (re-verified green)
US-017 | Research MCP | Poll traffic session | mcp_server.get_browser_traffic_session | As a host, I poll whether a session request was approved. | Returns the session row with current status (requested/approved/declined/stopped/expired). | get_browser_traffic_session(session_id) | Unknown session raises 'was not found'. Expired requests flip to expired. | Documented | PASS |  |  | PASS (re-verified green)
US-018 | Research MCP | Assignment prompt | mcp_server.research_assignment | As a host, I load a reusable workflow prompt for a research assignment. | Returns a numbered workflow: create job, connector_status, try fallbacks on not_configured, never dead-end, export at end, cite. | research_assignment(brief, decision) [MCP prompt] | Prompt must mention not_configured fallbacks and export_research_report. | Documented | PASS |  |  | PASS (re-verified green)
US-019 | Planner | Plan any brief | planner.build_plan | As a host, I get a source-agnostic plan from a brief. | Returns objective, decision, market, audience, deliverable, entities, research_questions, query_families, recommended_sources, source_queries, clarifications, exclusions. | build_plan(brief, decision, market, time_horizon, audience, deliverable, required_sources, exclusions) | Commercial briefs add a creative-territories question. Gaming briefs add twitch/kick/discord. required_sources lead. Too-short brief raises. | Documented | PASS |  |  | PASS (re-verified green)
US-020 | Store | Evidence dedup | store.add_evidence | As a host, repeated identical findings do not create duplicate evidence. | content_hash=sha256(source_type,url,excerpt); ON CONFLICT (job_id,content_hash) updates collected_at. | store.add_evidence(...) | Same content -> one row, collected_at refreshed. | Documented | PASS |  |  | PASS (re-verified green)
US-021 | Store | Dossier coverage & gaps | store.dossier | As a host, I see per-source counts and which recommended sources are still empty. | coverage counts by source_type; gaps = plan.recommended_sources with no evidence. | store.dossier(job_id) | Datetimes ISO-formatted; content_hash removed. | Documented | PASS |  |  | PASS (re-verified green)
US-022 | Store | List raw responses | store.list_raw_responses | As a host/export, I retrieve the raw HTTP payloads captured for a job. | Returns raw_responses rows for research_job_id ordered by received_at. | store.list_raw_responses(job_id) | Empty list when none captured. | Documented | PASS |  |  | PASS (re-verified green)
US-023 | Connectors | No dead-end fallbacks | connectors.not_configured | As a host, an unconfigured connector tells me the next door instead of failing. | Returns {not_configured:true, connector, error, setup, fallbacks[], next_step}. | any connector without creds | Every guide with credentials has >=1 fallback. | Documented | PASS |  |  | PASS (re-verified green)
US-024 | Connectors | SSRF URL validation | connectors._validate_public_url | As an operator, private/local/reserved targets cannot be crawled. | Rejects non-http(s), unresolvable, and non-global IPs; revalidates final URL after redirect. | crawl_web_page / fetch_rss | localhost/127.0.0.1/file:// rejected. | Documented | PASS |  |  | PASS (re-verified green)
US-025 | Connectors | Raw traffic logging | raw_log.record_raw | As an operator, connector HTTP payloads are stored redacted for provenance. | Stores redacted payload in raw_responses keyed by research_job_id; dedups by body_hash; best-effort (never breaks a connector). | automatic in each connector | Secrets in URL/headers/oauth body redacted; >2MB truncated with marker. | Documented | PASS |  |  | PASS (re-verified green)
US-026 | Export | Per-job export files | export.export_job | As a user, I export a job to shareable files. | Creates folder with report.md, report.html, evidence.json, evidence.csv, raw_responses.jsonl. | export_research_report / control center | Slug from brief; pipes escaped; CSV guards =+-@ cells. | Documented | PASS |  | Added job_folder() helper so 'Open folder' reuses an existing export. | PASS (re-verified; export files intact)
US-027 | Export | Gaps unlock section | export._gaps | As a user, the report tells me how to unlock each empty source. | For each gap, maps source->connector guide and lists setup + fallbacks in report.md. | export output | rss/web always-ready gaps show scope not creds. | Documented | FAIL | F2 (UX): export gap section renders an empty heading (e.g. '### rss') for always-ready sources that have no setup/fallbacks — reads as a bare, confusing heading. | Gap section now renders the connector guide's scope for always-ready sources (rss/web) instead of an empty heading. | PASS (test_always_ready_source_gap_has_guidance_not_empty_heading)
US-028 | Capture | Create pairing code | capture.create_pairing_code | As a user, I generate a one-time code to pair the extension. | Creates a hashed, 10-min single-use code; returns {pairing_code, expires_at}. | control center 'Create pairing code' | TTL clamped 1..30 min. | Documented | PASS |  |  | PASS (re-verified green)
US-029 | Capture | Exchange pairing code | capture.exchange_pairing_code | As the extension, I trade a code + extension id for a bearer token. | Single-use code -> stores hashed token bound to extension id; returns {client_id, token, extension_id}. | extension pairing | Reused/expired code rejected. Invalid extension id rejected. | Documented | PASS |  |  | PASS (re-verified green)
US-030 | Capture | Authenticate + origin bind | capture.authenticate | As the server, I accept only the paired extension origin or local UI. | Validates token hash (constant-time) and origin allowlist; updates last_used. | every capture request | Hostile origin -> PermissionError. Revoked token -> PermissionError. | Documented | PASS |  |  | PASS (re-verified green)
US-031 | Capture | Revoke client | capture.revoke_client | As a user, I revoke a paired browser immediately. | Sets revoked_at; subsequent auth and submissions fail. | POST /api/capture/revoke | Double revoke raises 'not found or already revoked'. | Documented | PASS |  |  | PASS (re-verified green)
US-032 | Capture | Capture mission | capture.mission | As the extension, I get the mission terms for the active job. | Returns brief, research_questions, look_for terms, exclusions for an active job. | GET /api/capture/jobs/{id}/mission | Inactive/unknown job raises 'was not found'. | Documented | PASS |  |  | PASS (re-verified green)
US-033 | Capture | Submit candidate | capture.submit | As a researcher, I queue a selected/scanned excerpt for review (not saved yet). | Inserts a pending browser_captures row with anonymized author; audit 'capture.submitted'. | POST /api/capture/pending | Bad url/excerpt/mode/question rejected. Author anonymized by default. | Documented | PASS |  |  | PASS (re-verified green)
US-034 | Capture | Review approve/reject | capture.review | As a researcher, I approve one candidate to promote it to evidence, or reject it. | Approve -> dedup insert into research_evidence, scrub staging; reject -> discard; audit event. | POST/DELETE /api/capture/pending/{id} | Other client cannot see/mutate. Already-reviewed raises. | Documented | PASS |  |  | PASS (re-verified green)
US-035 | Capture | Direct approve (idempotent) | capture.approve_direct | As the extension, I atomically submit+approve a capture, safe to retry. | Advisory-locked; idempotent by client_capture_id; promotes evidence; audit 'capture.approved'. | POST /api/capture/approve | Retry returns idempotent:true, same evidence_id. | Documented | PASS |  |  | PASS (re-verified green)
US-036 | Capture | Delete capture/evidence | capture.delete_capture | As a researcher, I delete a promoted capture and its evidence. | Deletes evidence + scrubs/deletes staging, client-scoped; audit 'capture.deleted'. | DELETE /api/capture/evidence/{id} | Wrong client cannot delete. | Documented | PASS |  |  | PASS (re-verified green)
US-037 | Capture | Expire pending | capture.expire_pending | As the system, stale pending candidates are purged. | Pending past expires_at -> status expired, content scrubbed; audit 'capture.expired'. | automatic on list | 24h default TTL. | Documented | PASS |  |  | PASS (re-verified green)
US-038 | Sessions | Request session | capture.request_session | As a host, I request an approval-gated traffic session for one domain. | Creates 'requested' session; normalizes domain; rejects duplicates and inactive jobs. | request_browser_traffic_session | scheme/port/path/IP/localhost rejected; dup live session rejected. | Documented | PASS |  |  | PASS (re-verified green)
US-039 | Sessions | Approve session | capture.approve_session | As a researcher, I approve a session once, binding it to my browser for <=30 min. | Sets approved, client_id, expires_at=now+min(ttl,30); returns session summary; audit 'session.approved'. | POST /api/capture/sessions/{id}/approve | Requires approved_by_user; revoked client rejected; only 'requested' approvable. | Documented | PASS |  |  | PASS (re-verified green)
US-040 | Sessions | Decline session | capture.decline_session | As a researcher, I decline a session request. | Sets declined; audit 'session.declined'. | POST /api/capture/sessions/{id}/decline | Only 'requested' declinable. | Documented | PASS |  |  | PASS (re-verified green)
US-041 | Sessions | Stop session | capture.stop_session | As a researcher, I stop an active session immediately from extension or control center. | Sets stopped, ended_at; audit 'session.stopped'; web UI may stop without client id. | POST /api/capture/sessions/{id}/stop or /api/research/sessions/{id}/stop | Only open sessions stoppable. | Documented | PASS |  |  | PASS (re-verified green)
US-042 | Sessions | Consent-gate enforcement | capture.approve_direct (approved_session) | As the server, I accept approved_session captures only while a live session covers the domain. | Requires metadata.session_id matching an approved, unexpired session for client+job whose domain covers URL host, else PermissionError. | POST /api/capture/approve (approved_session) | Pre-approval, wrong domain, expired, stopped all blocked. | Documented | PASS |  |  | PASS (re-verified green)
US-043 | Sessions | Network raw promotion | capture.approve_direct (network) | As the server, captured network payloads are stored redacted and summarized on evidence. | metadata.network -> record_raw_parts(browser_network) in same txn; evidence keeps bounded summary only (no body). | network capture approve | Body capped at session max_payload_bytes; secret query params redacted. | Documented | PASS |  |  | PASS (re-verified green)
US-044 | Sessions | Expire sessions | capture.expire_sessions | As the system, unapproved requests and past-expiry sessions are expired. | requested>10min or approved past expires_at -> expired; audit 'session.expired'. | automatic on list/status/active | active_session returns None when expired. | Documented | PASS |  |  | PASS (re-verified green)
US-045 | CLI | Migrate database | main.py migrate | As an operator, I initialize/upgrade the database. | Applies pending migrations and seeds config; prints 'Database migrated and configuration seeded.' | python main.py migrate | Idempotent; re-run skips applied migrations. | Documented | PASS |  |  | PASS (re-verified green)
US-046 | CLI | Collect a source | main.py collect | As an operator, I run one collector or all usable collectors. | Runs discord/twitch/kick/press or 'all'; prints completion; exits non-zero if any collector failed. | python main.py collect {discord¦twitch¦kick¦press¦all} | 'all' omits twitch/kick without creds. Single twitch/kick without creds fails that collector only. | Documented | PASS |  |  | PASS (re-verified green)
US-047 | CLI | Weekly report | main.py report | As an operator, I render a week's WoW rollup report. | Renders report.md + report.html for the ISO week; prints both paths. | python main.py report <YYYY-MM-DD Monday> | week_start must be a valid Monday, else arg-parse error before DB access. Overwrites same-week file. | Documented | PASS |  |  | PASS (re-verified green)
US-048 | CLI | Fresh signal pulse | main.py pulse | As an operator, I collect fresh signals now and render a brief scoped to this run. | Collects on_demand sources, renders fresh-signals brief for new run ids; prints path. | python main.py pulse [--sources ...] [--press-hours N] | --sources validated against known names; --press-hours must be >0. Brief still renders on collector failure then exits non-zero. | Documented | PASS |  |  | PASS (re-verified green)
US-049 | CLI | Replay raw responses | main.py replay | As an operator, I reparse stored raw responses offline (no network). | Reparses one response id or all ids of a run; prints 'Replayed raw response <id>'. | python main.py replay (--response-id N ¦ --run-id N) | Exactly one of the two required. Empty run set or per-id failures exit non-zero. | Documented | PASS |  |  | PASS (re-verified green)
US-050 | Collectors | Resilient HTTP client | collectors.base.HTTPClient | As an operator, collector HTTP is rate-limited, retried, and redaction-logged. | Bounded retries on 429/5xx/timeouts with Retry-After backoff; every response logged redacted to raw_responses. | internal to collectors | Secrets in headers/url/oauth body redacted. Raw evidence on a dedicated connection. | Documented | PASS |  |  | PASS (re-verified green)
US-051 | Collectors | Run logging | collectors.base.RunLog | As an operator, each collection run records status and counts. | Opens collection_runs row; final status success/partial/failed by outcome; errors truncated 1000 chars. | internal | Raw logging on separate connection survives collector rollback. | Documented | PASS |  |  | PASS (re-verified green)
US-052 | Collectors | Discord snapshots | collectors.discord.collect | As an operator, I snapshot public Discord invite/widget metadata for watchlisted servers. | Iterates active discord_servers, stores member/presence snapshots; dead invites flagged. | python main.py collect discord | 404 invite -> status invite_dead. Widget errors stored as unavailable. | Documented | PASS |  |  | PASS (re-verified green)
US-053 | Collectors | Twitch category snapshots | collectors.twitch.collect | As an operator, I snapshot Twitch stream/category viewership. | OAuth, paginates streams + games/top, upserts categories, inserts category_snapshots with directory rank. | python main.py collect twitch | 401 refreshes token once. Missing creds -> collector fails. | Documented | PASS |  |  | PASS (re-verified green)
US-054 | Collectors | Kick category snapshots | collectors.kick.collect | As an operator, I snapshot Kick livestream/category viewership. | OAuth, paginates livestreams, ranks categories by viewers, inserts snapshots. | python main.py collect kick | 401 refreshes token once. Missing creds -> collector fails. | Documented | PASS |  |  | PASS (re-verified green)
US-055 | Collectors | Press article ingestion | collectors.press.collect | As an operator, I ingest matching press articles from configured outlets. | Resolves each outlet feed, matches titles by alias, inserts deduped articles. | python main.py collect press | Unresolvable feed -> source unavailable. url_hash dedup. | Documented | PASS |  |  | PASS (re-verified green)
US-056 | Collectors | Offline replay | collectors.replay.replay_response | As an operator, I reparse a stored payload without hitting the network. | Dispatches by payload_kind, writes parsed/parse_status; never makes network calls. | python main.py replay | Unknown kind -> unsupported. Handler error -> failed + error stored. | Documented | PASS |  |  | PASS (re-verified green)
US-057 | Reporting | Weekly WoW report | reporting.render.render_report | As an operator, I get a week-over-week markdown+HTML report. | Builds rollup, renders template, writes <isoweek>-gaming-pulse.md/.html, logs report_runs. | python main.py report / control center | Coverage line 'N of 7 complete days'. Standalone HTML with inline CSS. | Documented | PASS |  |  | PASS (re-verified green)
US-058 | Reporting | Fresh signal brief | reporting.ondemand.render_signal_brief | As an operator, I get a brief of the freshest observations. | Renders <timestamp>-fresh-signals.md scoped to given run ids or latest snapshots. | python main.py pulse / control center | Empty sections emit placeholder rows. | Documented | PASS |  |  | PASS (re-verified green)
US-059 | Reporting | WoW rollup logic | reporting.rollup.build_rollup | As an operator, movement is only shown with enough clean coverage. | Movement states UP/DOWN/UNCHANGED/NEW/DROPPED/INSUFFICIENT_DATA/BASELINE; movers need >=2 sources agreeing. | internal to report | Needs >=5 clean scheduled days/week else INSUFFICIENT_DATA; fresh install -> BASELINE. | Documented | PASS |  |  | PASS (re-verified green)
US-060 | Config | Settings validation | settings.Settings | As an operator, invalid config is rejected early. | database_url required; collection_hour_utc 0-23; timeout>0; retries>=0; page bounds enforced. | loaded from .env | Missing DATABASE_URL raises at Settings(). | Documented | PASS |  |  | PASS (re-verified green)
US-061 | Config | Seed configuration | db.queries.seed_config | As an operator, titles/servers/outlets are seeded idempotently. | Upserts titles, discord_servers, press sources from config files. | python main.py migrate | Config files parsed as JSON; ON CONFLICT updates. | Documented | PASS |  |  | PASS (re-verified green)
US-062 | Control Center | Open dashboard | control_center serve-ui + main | As a user, I open the local dashboard in my browser. | Binds 127.0.0.1:8765, serves single-page UI with fresh session token, auto-opens browser. | double-click Open / python control_center.py | Port in use -> friendly SystemExit. | Documented | PASS |  |  | PASS (re-verified green)
US-063 | Control Center | System check | control_center.health /api/status | As a user, I see readiness and which connectors are configured. | Shows Setup file, Database, and optional connector statuses; readiness gated on DB. | UI loads / 'Check again' | Only cred presence checked, not live validity. | Documented | PASS |  |  | PASS (re-verified green)
US-064 | Control Center | Save setup | control_center.save_settings /api/settings | As a user, I save the database address and optional credentials. | Validates DB required + hour 0-23; writes .env at 0600; blank fields preserve existing secrets. | Setup dialog 'Save and prepare database' | Blank credential = keep saved. Only whitelisted keys written. | Documented | PASS |  |  | PASS (re-verified green)
US-065 | Control Center | Get fresh signals | control_center /api/run pulse | As a user, I collect fresh signals now. | Starts a background pulse subprocess; UI polls job status until done. | 'Get fresh signals' button | Gated on state.ready else opens Setup. 30-min timeout. | Documented | PASS |  |  | PASS (re-verified green)
US-066 | Control Center | Collect everything | control_center /api/run collect | As a user, I run a full collection snapshot. | Starts background collect-all subprocess. | 'Collect everything' button | Gated on ready. | Documented | PASS |  |  | PASS (re-verified green)
US-067 | Control Center | Create weekly report | control_center /api/run report | As a user, I generate this week's report. | Starts background report subprocess for the current Monday week. | 'Create weekly report' button | Gated on ready. | Documented | PASS |  |  | PASS (re-verified green)
US-068 | Control Center | Open report/folder | control_center.open_path /api/open | As a user, I open a report or the output folder in my file browser. | Opens weekly/fresh/output/research target cross-platform. | 'Open weekly/fresh/output' + per-job 'Open folder' | No report -> friendly error. research kind re-exports first. | Documented | PASS |  | 'Open folder' for a research job now opens the existing folder via job_folder(); exports only when the folder is absent (no longer re-exports on every click). | PASS (test_open_research_folder_reuses_existing_export)
US-069 | Control Center | Research jobs panel | control_center /api/research/jobs + export | As a user, I list research jobs and export any to files. | Lists up to 50 jobs; per-job Export writes folder; Open opens it. | Research jobs panel buttons | Export requires X-Pulse-Token. job_id<=0 rejected. | Documented | PASS |  |  | PASS (re-verified green)
US-070 | Control Center | Create pairing code | control_center /api/capture/pairing-code | As a user, I create a one-time code to pair the extension. | Returns a 10-min single-use code shown in the UI. | 'Create one-time pairing code' button | Gated on ready else opens Setup. | Documented | PASS |  |  | PASS (re-verified green)
US-071 | Control Center | Job progress polling | control_center start_job/run_job /api/job | As a user, I see live progress of a running action. | Background thread runs subprocess; UI polls /api/job every 1s until non-running. | automatic after run | Unknown job id -> 404. Details capped 4000 chars. | Documented | PASS |  |  | PASS (re-verified green)
US-072 | Control Center | Session token security | control_center X-Pulse-Token | As a user, stale dashboard sessions can't mutate state. | Mutating POSTs require the per-process token; after restart the old page gets 403 refresh prompt. | any mutating action | Token rotates each restart. | Documented | PASS |  |  | PASS (re-verified green)
US-073 | Control Center | Origin/host guard | control_center.capture_client + do_OPTIONS | As an operator, only the paired extension origin and exact local host are accepted. | Capture requests require exact Host + chrome-extension origin; CORS preflight limited to that origin. | extension requests | Hostile origin/host -> 403. | Documented | PASS |  |  | PASS (re-verified green)
US-074 | Control Center | Rate limiting | control_center.enforce_rate | As an operator, capture and pairing endpoints are rate-limited. | Sliding 60s window: capture 120/min per token, pair 10/min per extension id. | capture/pair requests | Exceed -> 'Too many' 403. | Documented | PASS |  |  | PASS (re-verified green)
US-075 | Extension Options | Pair browser | options.pair | As a user, I pair the extension with a one-time code. | POSTs code to /api/capture/pair, stores token+baseUrl. | Options 'Pair browser' | Empty code -> error. baseUrl forced local http. | Documented | PASS |  |  | PASS (re-verified green)
US-076 | Extension Options | Unpair browser | options.unpair | As a user, I unpair and revoke this browser. | Confirms, calls revoke, clears token/job/candidates. | Options 'Unpair' | Revoke failure keeps token. | Documented | PASS |  |  | PASS (re-verified green)
US-077 | Extension Options | Save options | options.save | As a user, I set base URL, anonymize default, and max candidates. | Persists settings; maxCandidates clamped 1-25. | Options 'Save settings' | Invalid baseUrl -> error. | Documented | PASS |  |  | PASS (re-verified green)
US-078 | Extension Popup | Load jobs | popup.loadJobs | As a researcher, I pick the active research job. | Fetches active jobs into the dropdown. | popup open / refresh | No token -> 'Pair this extension in Settings first.' | Documented | PASS |  |  | PASS (re-verified green)
US-079 | Extension Popup | Load mission | popup.loadMission | As a researcher, I see the mission questions and look-for terms. | Fetches mission, fills question dropdown and mission text. | after selecting a job | No job -> disabled question. | Documented | PASS |  |  | PASS (re-verified green)
US-080 | Extension Popup | Scan visible | popup.scan + content.js | As a researcher, I queue visible on-page passages matching the mission. | Injects content.js, scans visible passages, queues candidates for review. | 'Find visible candidates' | Blocked when stopped/no job/non-http tab; caps at 25; no match -> warning. | Documented | PASS |  |  | PASS (re-verified green)
US-081 | Extension Popup | Right-click capture | background context-menu-review | As a researcher, I queue a highlighted selection for review. | Context menu queues the selection as a candidate, badge '1'. | right-click 'Review in Research Oyster' | Blocked if stopped or no active job. | Documented | PASS |  |  | PASS (re-verified green)
US-082 | Extension Popup | Review approve | popup.approve | As a researcher, I approve one candidate to save it as evidence. | POSTs approval; only Approve saves; removes card. | 'Approve & save' | Blocked if candidate job != active job; empty excerpt blocked. | Documented | PASS |  |  | PASS (re-verified green)
US-083 | Extension Popup | Review reject/clear | popup.reject/clearAll | As a researcher, I discard candidates locally. | Reject removes one; Clear all discards the queue (confirm). | 'Reject' / 'Clear all' | No server call; queue local. | Documented | PASS |  |  | PASS (re-verified green)
US-084 | Extension Popup | Stop/resume collection | popup.toggleStop | As a researcher, I halt all new captures instantly. | Toggles global stopped state; blocks scan/context-menu/network capture; queue kept. | 'Stop' / 'Resume' | Global across capture types. | Documented | PASS |  |  | PASS (re-verified green)
US-085 | Extension Popup | Anonymize toggle | popup.toggleAnonymize | As a researcher, I toggle name redaction per candidate. | Re-derives excerpt from raw via anonymize() or restores raw. | per-card checkbox | raw_excerpt is source of truth. | Documented | PASS |  |  | PASS (re-verified green)
US-086 | Extension Popup | Session approve | popup.approveSession + background.startSession | As a researcher, I approve a traffic session and start recording. | Approves session, requests Chrome host permission, injects recorder, sets expiry alarm. | 'Approve (30 min)' on request card | Declined Chrome permission -> nothing recorded (double consent). | Documented | PASS |  |  | PASS (re-verified green)
US-087 | Extension Popup | Session decline | popup.declineSession | As a researcher, I decline a traffic session request. | Declines the requested session. | 'Decline' on request card | Only requested sessions. | Documented | PASS |  |  | PASS (re-verified green)
US-088 | Extension Popup | Session stop | popup.stopSession + background.stopSession | As a researcher, I stop recording immediately. | Stops session, removes host permission, clears alarm/state. | 'Stop recording' | Tolerant if server already ended it. | Documented | PASS |  |  | PASS (re-verified green)
US-089 | Extension Background | Network capture recorder | background.handleNetworkCapture + session_recorder | As a researcher, an approved session captures the page's own JSON responses. | Recorder surfaces same-domain JSON; worker dedupes, extracts messages, POSTs approved_session evidence. | automatic during approved session | Domain must match; max 50/session; 403 -> auto-stop; never reads cookies/headers. | Documented | PASS |  |  | PASS (re-verified green)
US-090 | Extension Background | Session auto-expiry | background.alarm-expiry | As a researcher, a session ends automatically at its TTL. | Alarm at expiry auto-stops the session. | automatic | Matches oyster-session-<id> alarm. | Documented | PASS |  |  | PASS (re-verified green)
US-091 | Launcher | Install (macOS) | Install Gaming Pulse.command | As a Mac user, I one-click install everything. | Installs brew deps + Postgres, creates DB + venv, writes .env, migrates, opens control center. | double-click Install | macOS-only; brew prompt; PG-start failure guidance. | Documented | PASS |  |  | PASS (re-verified green)
US-092 | Launcher | Open control center | Open Gaming Pulse.command | As a Mac user, I reopen the dashboard. | Execs control_center.py. | double-click Open | Missing .venv/.env -> 'Install first' alert. | Documented | PASS |  |  | PASS (re-verified green)
US-093 | Launcher | Attach MCP | Attach Research Oyster.command | As a Mac user, I attach Oyster to my AI host. | Registers research-oyster-mcp with Codex and/or Claude Code. | double-click Attach | No host on PATH -> 'No supported AI host found'. | Documented | PASS |  |  | PASS (re-verified green)
US-094 | Control Center | Active capture sessions panel | control_center.sessions-panel | As a user, I see and stop active browser traffic sessions from the dashboard. | The control center lists open capture sessions and offers a Stop button (web-token). | Research jobs area of the dashboard | Uses GET /api/research/sessions + POST /api/research/sessions/{id}/stop. | Documented | FAIL | F1 (UX): control center exposes /api/research/sessions + /stop but no dashboard panel/JS calls them; researcher cannot see or stop a traffic session from the control center. | Added 'Active capture sessions' panel + loadResearchSessions()/stopResearchSession() JS calling GET /api/research/sessions and POST /api/research/sessions/{id}/stop; wired into refresh(). | PASS (http probe green; test_active_sessions_panel_is_wired_in_the_ui)
US-095 | Sessions | Trust a domain (standing consent) | capture.trust_domain | As a researcher, I approve a domain once so future capture sessions on it start hands-free. | Records per-client standing consent; requires approved_by_user + Chrome host permission; revocable and audited. | Extension settings 'Trust domain' / 'Always capture this domain' | Bare public domain only; scheme/port/IP/localhost rejected. | Documented | PASS |  | Built this session | PASS (test_trusted_domain_auto_approves_only_matching_sessions; test_standing_consent_trusts_domain_and_auto_approves; JS syntax-checked + core tests)
US-096 | Sessions | List/revoke trusted domains | capture.list_trusted_domains | As a researcher, I see and remove the domains I've trusted. | Lists active trusted domains; untrust revokes and stops future auto-approval; unpair clears all. | Extension settings list + Remove | Per-client; cascade-cleared on client delete. | Documented | PASS |  | Built this session | PASS (test_trusted_domain_auto_approves_only_matching_sessions; test_standing_consent_trusts_domain_and_auto_approves; JS syntax-checked + core tests)
US-097 | Sessions | Auto-approve trusted sessions | capture.auto_approve_for_client | As a researcher, requested sessions on my trusted domains approve automatically. | Approves only requested sessions whose domain the client trusts; each keeps its own 30-min TTL; audited as standing_consent. | Extension auto-approve poll (1 min) + popup open | Untrusted-domain sessions stay 'requested'; never opens/navigates tabs. | Documented | PASS |  | Built this session | PASS (test_trusted_domain_auto_approves_only_matching_sessions; test_standing_consent_trusts_domain_and_auto_approves; JS syntax-checked + core tests)
US-098 | Sessions | Standing-consent recording | background.autoApproveTick + startTrustedSession | As a researcher, capture starts on trusted domains on tabs I already have open. | Poll approves + injects recorder into open tabs on the domain; onUpdated re-injects on navigation; Stop/TTL still apply. | automatic while browsing a trusted domain | Never headless/unattended; blocked while collection stopped; permission kept until untrust. | Documented | PASS |  | Built this session | PASS (test_trusted_domain_auto_approves_only_matching_sessions; test_standing_consent_trusts_domain_and_auto_approves; JS syntax-checked + core tests)
US-099 | Launcher | One-line installer | install.sh | As a new user, I install everything with a single pasted command. | curl¦bash: clones repo, installs Python+Postgres if missing (macOS brew / Linux apt), creates+migrates db, writes .env, attaches MCP to Claude/Codex, opens dashboard. Idempotent; never overwrites .env/db. | curl -fsSL .../install.sh ¦ bash | macOS needs Homebrew; runs as root or via sudo; OYSTER_HOME/BRANCH/REPO overridable; extension still loaded once manually. | Documented | PASS |  | Built this session | PASS (ran end-to-end in a clean temp location: clone->db->migrate->attach->exit 0; bash -n clean)

## Summary
Research Oyster — Feature Status Summary
Metric | Count
Total user stories
Phase 1 documented
Phase 2 tested (non-blank)
Phase 2 PASS
Phase 2 FAIL
Errors logged
Fixes applied
Phase 4 PASS
Area | Stories
Research MCP
Planner
Store
Connectors
Export
Capture
Sessions
CLI
Collectors
Reporting
Config
Control Center
Extension Options
Extension Popup
Extension Background
Launcher

## Legend
How to read this workbook
This is the single canonical tracker for every Research Oyster feature.
Columns:
Phase 1 Status — 'Documented' once the user story + expected behaviour are written.
Phase 2 Test Result — 'PASS' or 'FAIL: <why>' after testing the story against the code.
Errors Found — any logistical/UX/logic error observed during Phase 2.
Phase 3 Fix — what was changed to resolve the error (commit-level).
Phase 4 Retest — 'PASS' after re-testing post-fix (or 'N/A' if nothing to fix).
The Summary sheet counts each status live with formulas.
IDs are stable (US-001..). Areas are colour-tagged on the User Stories sheet.